## Sheet1
Test # | Rqmt | Subsystem | Purpose | Input Data | Expected Results | Pass/Fail | Error Handeling
1 | 2.2.1 | Login | Login as admin. | Email: lc@test.com | User logs in and accesses all pages. | Pass
Password: 123
2 | 2.2.1 | Login | Login as manager. | Email: md@test.com | User logs in and accesses all pages. | Pass
Password: 123
3 | 2.2.1 | Login | Login as sales. | Email: jj@test.com | User logs in and accesses all pages except Admin and Accounts pages. | Pass
Password: 123
4 | 2.2.1 | Login | Login as deactivated. | Email: dr@test.com | User cannot log in and an explanation is provided. | Pass
Password: 123
5 | 2.2.2 | Logout | Logout as sales. | Click Logout on the header. | The login page appears. | Pass
6 | 2.2.3 | Products | Display page. | Click the display page. | Three searchable fields and no results are displayed until searched. | Pass
7 | 2.2.3 | Products | Return product search results. | Use the product name (BG CF5), number (PN 203), and warehouse id (0 to 5) to search for a variety of results. | Found results are listed in a table. Results not found is handled correctly. | Pass
8 | 2.2.8 | Admin | Display page. | Click Admin on the menu bar. | Observe Admin page with Accounts link. | Pass
9 | 2.2.8 | Accounts | Display page. | Click Accounts on the Admin page. | Observe the list of system users and related information. | Pass
10 | 2.2.8 | Accounts | Create (good) user. | Create user with a variety of inputs (warehouse id is optional). | Created user is displayed on the Accounts page. | Pass
11 | 2.2.8 | Accounts | Create (bad) user. | Create user with duplicate or missing information. | Acceptable error is displayed on the Accounts page. | Pass
12 | 2.2.8 | Accounts | Create user (cancelled). | Create user but click Cancel. | Transaction is not completed and user is returned to the Accounts page. | Pass
13 | 2.2.9 | Accounts | Update (good) user. | Update user with a variety of inputs (password and warehouse id is optional). Email cannot be changed. | Updated user is displayed on the Accounts page. | Pass
14 | 2.2.9 | Accounts | Update (bad) user. | Update user with duplicate or missing information. | Acceptable error is displayed on the Accounts page. | Pass | Missing information worked, but was able to update full name to match another user (I do not know if this is allowed or not)
15 | 2.2.9 | Accounts | Update user (cancelled). | Update user but click Cancel. | Transaction is not completed and user is returned to the Accounts page. | Pass
16 | 2.2.10 | Accounts | Disable user. | Update a user, changing role to “Disabled”. Click Update. | Observe the user account is disabled on the Accounts page. | Pass | If by disable you mean deactivated, then it works
17 | 2.2.5 | Customers | Display Page. | Click Customers in the nav bar. | List of all customers in alphabetical order by name. All should have update buttons. | Pass
18 | 2.2.5 | Customers | Create new customer. | Select new customer on customer display page. Fill out form with appropriate values. | Return to the customer display page with an indicator of success or failure. If success the new customers info should be in the list. | Pass
19 | 2.2.5 | Customers | Update customer information. | Select update on one customer from the display page. Make some changes to the form. Select Submit. | Return to the customer display page and see that the customer’s information has been updated. | Pass
20 | 2.2.4 | File Import | Import page. | Select Import in the nav bar. | Displays import page which includes a file upload form and example of each type of possible transaction that can be in a file. | Pass
21 | 2.2.4 | File Import | Select File | Select the browse button. | A file selector window. The file name should appear on the input page after selection. | Pass
22 | 2.2.4 | File Import | Cancel Selection | After selecting a file, click the cancel button. | The file name should disappear. | Pass
23 | 2.2.4 | File Import | Upload file that performs some warehouse transactions successfully. | The example file included in appendix B1 or a custom file made by the testing team. | On selecting upload the system should give a message indicating success. | Fail | Program claimed successful upload, but when we checked the product page, nothing had changed
24 | 2.2.4 | File Import | Upload file that has errors and fails system validation. | The example file included in appendix B1 run a second time or some custom file made by the testing team. | On selecting browse you should be able to upload a local file to the system. After selecting upload the system should give a message indicating failure and enumerate the file errors. | Pass
25 | 2.2.5 | Invoice metrics | Render create invoice page. | Select invoice in the navigation bar, then select CREATE button. | Should render a web form with the following fields; Customer ID, Product Part Number, and Qty. | Pass
26 | 2.2.5 | Invoice creation | Add line item to invoice form. (Success) | Fill out both product di number and quantity fields then select ADD ANOTHER LINE. | On Selecting the ADD ANOTHER LINE button, another two fields should appear below the original product part number and quantity fields. | Pass
27 | 2.2.5 | Invoice creation | Add line item to invoice form. (Error) | Do not fill out product number id field then select ADD ANOTHER LINE. | On selecting the ADD ANOTHER LINE button, a javascript alert informs the user that their previous line item’s product id is still empty. | Fail | Another line was added even though previous product number was empty
28 | 2.2.5 | Invoice creation | Add line item to invoice form. (Error) | Fill out product number id field, but not the quantity field then select ADD ANOTHER LINE. | On selecting the ADD ANOTHER LINE button, a javascript alert informs the user that their previous line item’s quantity is still empty. | Fail | Another line was added even though previous Qty was empty
29 | 2.2.5 | Invoice creation | Create a hard copy .txt file of the actual invoice. (Success) | The create invoice page requires all four fields to be filled out to attempt invoice creation. Customer ID, Seller Email, Product Part Number, and Quantity Sold. | On selecting SUBMIT you should receive an alert indicating a successful submission. | Pass | Passed, but customer ID unclear what to type in
30 | 2.2.5 | Invoice creation | Create a hard copy .txt file of the actual invoice. (Error: incomplete form) | Leave any of the form fields empty. | On selecting SUBMIT you should be prompted to fill out the incomplete fields. The missing fields should also be highlighted. | Pass
31 | 2.2.5 | Invoice creation | Access hard copy of invoice. | Upon successful creation of invoice, follow link provided within alert. | Should behave as attachment and prompt user to download the invoice as a .txt file. | Pass | Passed, but auto downloaded as opposed to asking user if they wanted to download it
32 | 2.2.5 | Invoice creation | Create a hard copy .txt file of the actual invoice. (Error: Customer ID) | Enter a non existing customer id. | On selecting SUBMIT you should receive an alert indicating a there was an error followed by some additional information to help identify the error more specifically. | Fail | Internal Server Error; entered in nonexisting customer
33 | 2.2.5 | Invoice creation | Create a hard copy .txt file of the actual invoice. (Error: Seller) | Enter a non existing seller email. | On selecting SUBMIT you should receive an alert indicating a there was an error followed by some additional information to help identify the error more specifically. | Fail | Internal Server Error; entered non existing seller
34 | 2.2.5 | Invoice creation | Create a hard copy .txt file of the actual invoice. (Error: Product Part Number) | Enter a non existing product part number. | On selecting SUBMIT you should receive an alert indicating a there was an error followed by some additional information to help identify the error more specifically. | Fail | Internal Server Error; entered non existing product part number
35 | 2.2.5 | Invoice creation | Create a hard copy .txt file of the actual invoice. (Error: Quantity) | Enter a quantity greater than what is available in the corresponding warehouse. | On selecting SUBMIT you should receive an alert indicating a there was an error followed by some additional information to help identify the error more specifically. | Fail | Internal Server Error; entered quantity greater than what is available at the warehouse
36 | 2.2.7 | Invoice Metrics | Search Invoice Page | Select Invoice in the nav bar. Then select invoice search. | Should display a keyword input field and a date range input field and no results. | Pass
37 | 2.2.7 | Invoice Metrics | Invoice Search | Any search term and/or date range. This should handle any possible combination including empty fields. | A list of sales sorted by date that are within the given date range and are related in some way to the keyword search term. | Pass
Test # | Rqmt | Subsystem | Purpose | Usability (0-5) | Feedback
1 | 2.2.1 | Sessions | Login | 5
2 | 2.2.2 | Sessions | Logout | 5 | Logout could be made to look different from other tabs.
3 | 2.2.3 | Products | Search for Product | 4 | Works, but unless I was told, would not know what to put in last text field due to word being cut off
4 | 2.2.4 | Import | Import Inventory File | 5
5 | 2.2.5 | Invoice, Customers | Create Invoice | 3 | Passed when creating invoice, but got internal server errors when any information was typed incorrectly
6 | 2.2.6 | Invoice | Search for Invoice | 5
7 | 2.2.7 | Invoice | Sales Metric | 4
8 | 2.2.8 | Accounts | Create User | 5
9 | 2.2.9 | Accounts | Update User | 5
10 | 2.2.10 | Accounts | Disable User | 5